## Reconciling
Lake Elmo Drive - Main Street to Wicks Lane |  |  |  | C I T Y O F B I L L I N G S | [5 empty] | P R O G R E S S P A Y M E N T
Work Order 08-21 |  |  |  | CONTRACTOR ESTIMATE NUMBER: | [5 empty] | ESTIMATE PERIOD: |  | 2010-11-01
CONTRACTOR: Riverside Sand & Gravel |  |  |  | SUBMITTED BY: |  | Riverside Sand & Gravel |  |  |  | DATE PREPARED: |  | 2010-12-05 |  |  |  |  | PROJECT: W.O. 08-21 Lake Elmo Drive - Main St to Wicks Ln
C. O. : Seven (7) Reconciling (12/13/2010)
Schedule 1 |  |  | C O N T R A C T |  |  | THIS ESTIMATE |  | PRIOR ESTIMATES |  | T O D A T E |  |  | UNIT | Amount | C.O. Unit | Revised | Schedule 1
[13 empty] | CMPLTE | OverRun/ | Increase/ | Contract |  |  |  |  | Quantity |  | Dollar Amount
ITEM | DESCRIPTION | UNIT | QUANTITY | UNIT PRICE | AMOUNT | QUANTITY | AMOUNT | QUANTITY | AMOUNT | QUANTITY | AMOUNT | % OF BID | (X) | (UnderRun) | (Decrease) | Quantity | ITEM | DESCRIPTION | UNIT | UNIT PRICE | Increase / (Decrease) |  | Increase / (Decrease)
1 | MOBILIZATION | LS | 1 | 24250 | 24250 |  | 0 | 1 | 24250 | 1 | 24250 | 100% | X | 0 | 0 | 1 | 1 | MOBILIZATION | LS | 24250 | 0 | 0 | 0 | 0
2 | TAXES, BONDS, AND INSURANCE | LS | 1 | 4100 | 4100 |  | 0 | 1 | 4100 | 1 | 4100 | 100% | X | 0 | 0 | 1 | 2 | TAXES, BONDS, AND INSURANCE | LS | 4100 | 0 | 0 | 0 | 0
3 | TRAFFIC CONTROL | LS | 1 | 28500 | 28500 |  | 0 | 1 | 28500 | 1 | 28500 | 100% | X | 0 | 0 | 1 | 3 | TRAFFIC CONTROL | LS | 28500 | 0 | 0 | 0 | 0
4 | CLEARING AND GRUBBING | LS | 1 | 29000 | 29000 |  | 0 | 1 | 29000 | 1 | 29000 | 100% | X | 0 | 0 | 1 | 4 | CLEARING AND GRUBBING | LS | 29000 | 0 | 0 | 0 | 0
5 | REMOVE PAVEMENT | SY | 6900 | 2.75 | 18975 |  | 0 | 14095.43 | 38762.4325 | 14095.43 | 38762.4325 | 204.3% | X | 19787.4325 | 7195.43 | 14095.43 | 5 | REMOVE PAVEMENT | SY | 2.75 | 7195.43 | 0 | 19787.4325 | 0
6 | ITEM NOT USED IN THIS SCHEDULE | SY | 0 | [13 empty] | 6 | ITEM NOT USED IN THIS SCHEDULE | SY
7 | REMOVE CURB AND GUTTER | LF | 700 | 3.5 | 2450 |  | 0 | 872.6 | 3054.1 | 872.6 | 3054.1 | 124.7% | X | 604.1 | 172.6 | 872.6 | 7 | REMOVE CURB AND GUTTER | LF | 3.5 | 172.6 | 0 | 604.1 | 0
8 | CONCRETE FLATWORK REMOVAL | SY | 240 | 9.25 | 2220 |  | 0 | 757.05 | 7002.7125 | 757.05 | 7002.7125 | 315.4% | X | 4782.7125 | 517.05 | 757.05 | 8 | CONCRETE FLATWORK REMOVAL | SY | 9.25 | 517.05 | 0 | 4782.7125 | 0
9 | REMOVE STORM MANHOLE OR INLET | EA | 2 | 755 | 1510 |  | 0 | 2 | 1510 | 2 | 1510 | 100% | X | 0 | 0 | 2 | 9 | REMOVE STORM MANHOLE OR INLET | EA | 755 | 0 | 0 | 0 | 0
10 | ITEM NOT USED IN THIS SCHEDULE | LS | 0 | [13 empty] | 10 | ITEM NOT USED IN THIS SCHEDULE | LS
11 | REMOVE SIGNS | EA | 3 | 38 | 114 | 1 | 38 | 4 | 152 | 5 | 190 | 166.7% | X | 76 | 2 | 5 | 11 | REMOVE SIGNS | EA | 38 | 2 | 0 | 76 | 0
12 | REMOVE AND RESET PRIVATE SIGNS 15+60 | EA | 1 | 4400 | 4400 | 0.5 | 2200 | 0.5 | 2200 | 1 | 4400 | 100% | X | 0 | 0 | 1 | 12 | REMOVE AND RESET PRIVATE SIGNS 15+60 | EA | 4400 | 0 | 0 | 0 | 0
13 | REMOVE AND RESET PRIVATE SIGNS 20+60 | EA | 1 | 3625 | 3625 | 0.5 | 1812.5 | 0.5 | 1812.5 | 1 | 3625 | 100% | X | 0 | 0 | 1 | 13 | REMOVE AND RESET PRIVATE SIGNS 20+60 | EA | 3625 | 0 | 0 | 0 | 0
14 | REMOVE AND RESET PRIVATE SIGNS 27+20 | EA | 1 | 2470 | 2470 | 0.5 | 1235 | 0.5 | 1235 | 1 | 2470 | 100% | X | 0 | 0 | 1 | 14 | REMOVE AND RESET PRIVATE SIGNS 27+20 | EA | 2470 | 0 | 0 | 0 | 0
15 | ADJUST MANHOLE | EA | 11 | 200 | 2200 | 1 | 200 | 10 | 2000 | 11 | 2200 | 100% | X | 0 | 0 | 11 | 15 | ADJUST MANHOLE | EA | 200 | 0 | 0 | 0 | 0
16 | ADJUST WATER VALVE | EA | 13 | 295 | 3835 | 6 | 1770 | 13 | 3835 | 19 | 5605 | 146.2% | X | 1770 | 6 | 19 | 16 | ADJUST WATER VALVE | EA | 295 | 6 | 0 | 1770 | 0
17 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 17 | ITEM NOT USED IN THIS SCHEDULE | EA
18 | ADJUST INLET | EA | 1 | 270 | 270 |  | 0 | 1 | 270 | 1 | 270 | 100% | X | 0 | 0 | 1 | 18 | ADJUST INLET | EA | 270 | 0 | 0 | 0 | 0
19 | ADJUST FIRE HYDRANT | EA | 2 | 825 | 1650 |  | 0 | 3 | 2475 | 3 | 2475 | 150% | X | 825 | 1 | 3 | 19 | ADJUST FIRE HYDRANT | EA | 825 | 1 | 0 | 825 | 0
20 | RELOCATE CURB STOP | EA | 5 | 870 | 4350 |  | 0 | 4 | 3480 | 4 | 3480 | 80% | X | -870 | -1 | 4 | 20 | RELOCATE CURB STOP | EA | 870 | 0 | -1 | 0 | -870
21 | RELOCATE FIRE HYDRANT | EA | 1 | 1775 | 1775 |  | 0 | 0 | 0 | 0 | 0 | 0% | X | -1775 | -1 | 0 | 21 | RELOCATE FIRE HYDRANT | EA | 1775 | 0 | -1 | 0 | -1775
22 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 22 | ITEM NOT USED IN THIS SCHEDULE | EA
23 | EXCAVATION UNCLASSIFIED | CY | 3780 | 8.75 | 33075 |  | 0 | 3013 | 26363.75 | 3013 | 26363.75 | 79.71% | X | -6711.25 | -767 | 3013 | 23 | EXCAVATION UNCLASSIFIED | CY | 8.75 | 0 | -767 | 0 | -6711.25
24 | ITEM NOT USED IN THIS SCHEDULE | CY | 0 | [13 empty] | 24 | ITEM NOT USED IN THIS SCHEDULE | CY
25 | TEMPORARY EROSION CONTROL | LS | 1 | 3500 | 3500 |  | 0 | 1 | 3500 | 1 | 3500 | 100% | X | 0 | 0 | 1 | 25 | TEMPORARY EROSION CONTROL | LS | 3500 | 0 | 0 | 0 | 0
26 | CRUSHED AGGREGATE COURSE | CY | 3300 | 13 | 42900 |  | 0 | 3300 | 42900 | 3300 | 42900 | 100% | X | 0 | 0 | 3300 | 26 | CRUSHED AGGREGATE COURSE | CY | 13 | 0 | 0 | 0 | 0
27 | PLANT MIX BIT SURF GR B-MOD | TON | 2030 | 28 | 56840 |  | 0 | 2030 | 56840 | 2030 | 56840 | 100% | X | 0 | 0 | 2030 | 27 | PLANT MIX BIT SURF GR B-MOD | TON | 28 | 0 | 0 | 0 | 0
28 | ASPHALT CEMENT PG 64-22 | TON | 110 | 520 | 57200 |  | 0 | 107.64 | 55972.8 | 107.64 | 55972.8 | 97.85% | X | -1227.2 | -2.36 | 107.64 | 28 | ASPHALT CEMENT PG 64-22 | TON | 520 | 0 | -2.36 | 0 | -1227.2
29 | EMULSIFIED ASPHALT SS-1 | GAL | 440 | 3 | 1320 |  | 0 | 440 | 1320 | 440 | 1320 | 100% | X | 0 | 0 | 440 | 29 | EMULSIFIED ASPHALT SS-1 | GAL | 3 | 0 | 0 | 0 | 0
30 | CONCRETE CURB AND GUTTER/LAYDOWN CURB | LF | 4240 | 10 | 42400 |  | 0 | 4397.7 | 43977 | 4397.7 | 43977 | 103.7% | X | 1577 | 157.7 | 4397.7 | 30 | CONCRETE CURB AND GUTTER/LAYDOWN CURB | LF | 10 | 157.7 | 0 | 1577 | 0
31 | CONCRETE SIDEWALK (4-INCH) | SF | 10800 | 3.5 | 37800 |  | 0 | 13094.9 | 45832.15 | 13094.9 | 45832.15 | 121.2% | X | 8032.15 | 2294.9 | 13094.9 | 31 | CONCRETE SIDEWALK (4-INCH) | SF | 3.5 | 2294.9 | 0 | 8032.15 | 0
32 | CONCRETE SIDEWALK (6-INCH) | SF | 5400 | 4.75 | 25650 |  | 0 | 2492 | 11837 | 2492 | 11837 | 46.15% | X | -13813 | -2908 | 2492 | 32 | CONCRETE SIDEWALK (6-INCH) | SF | 4.75 | 0 | -2908 | 0 | -13813
33 | ITEM NOT USED IN THIS SCHEDULE | SY | 0 | [13 empty] | 33 | ITEM NOT USED IN THIS SCHEDULE | SY
34 | CONCRETE PEDESTRIAN RAMP (6-INCH) | SF | 990 | 5.75 | 5692.5 |  | 0 | 976.8 | 5616.6 | 976.8 | 5616.6 | 98.67% | X | -75.9 | -13.2 | 976.8 | 34 | CONCRETE PEDESTRIAN RAMP (6-INCH) | SF | 5.75 | 0 | -13.2 | 0 | -75.9
35 | DETECTABLE WARNING PANELS | SF | 64 | 26 | 1664 |  | 0 | 64 | 1664 | 64 | 1664 | 100% | X | 0 | 0 | 64 | 35 | DETECTABLE WARNING PANELS | SF | 26 | 0 | 0 | 0 | 0
36 | CONCRETE VALLEY GUTTER (6-INCH) | SF | 650 | 6.25 | 4062.5 |  | 0 | 463.3 | 2895.625 | 463.3 | 2895.625 | 71.28% | X | -1166.875 | -186.7 | 463.3 | 36 | CONCRETE VALLEY GUTTER (6-INCH) | SF | 6.25 | 0 | -186.7 | 0 | -1166.875
37 | CONCRETE DRIVEWAY APPROACH (6-INCH) | SF | 5310 | 5.75 | 30532.5 |  | 0 | 5607.2 | 32241.4 | 5607.2 | 32241.4 | 105.6% | X | 1708.9 | 297.2 | 5607.2 | 37 | CONCRETE DRIVEWAY APPROACH (6-INCH) | SF | 5.75 | 297.2 | 0 | 1708.9 | 0
38 | DRIVEWAY-ASPHALT | SY | 50 | 22 | 1100 |  | 0 | 692.5 | 15235 | 692.5 | 15235 | 1385% | X | 14135 | 642.5 | 692.5 | 38 | DRIVEWAY-ASPHALT | SY | 22 | 642.5 | 0 | 14135 | 0
39 | DRIVEWAY-CONCRETE | SF | 1950 | 5.75 | 11212.5 |  | 0 | 3796 | 21827 | 3796 | 21827 | 194.7% | X | 10614.5 | 1846 | 3796 | 39 | DRIVEWAY-CONCRETE | SF | 5.75 | 1846 | 0 | 10614.5 | 0
40 | RETAINING WALL | LF | 84 | 140 | 11760 |  | 0 | 107.4 | 15036 | 107.4 | 15036 | 127.9% | X | 3276 | 23.4 | 107.4 | 40 | RETAINING WALL | LF | 140 | 23.4 | 0 | 3276 | 0
41 | RETAINING WALL ADA | SF | 75 | 25 | 1875 |  | 0 | 114.7 | 2867.5 | 114.7 | 2867.5 | 152.9% | X | 992.5 | 39.7 | 114.7 | 41 | RETAINING WALL ADA | SF | 25 | 39.7 | 0 | 992.5 | 0
42 | PVC 6-IN SD | LF | 10 | 82 | 820 |  | 0 | 8 | 656 | 8 | 656 | 80% | X | -164 | -2 | 8 | 42 | PVC 6-IN SD | LF | 82 | 0 | -2 | 0 | -164
43 | PVC 12-IN SD | LF | 34 | 54 | 1836 |  | 0 | 34 | 1836 | 34 | 1836 | 100% | X | 0 | 0 | 34 | 43 | PVC 12-IN SD | LF | 54 | 0 | 0 | 0 | 0
44 | PVC 15-IN SD | LF | 11.5 | 83 | 954.5 |  | 0 | 37 | 3071 | 37 | 3071 | 321.7% | X | 2116.5 | 25.5 | 37 | 44 | PVC 15-IN SD | LF | 83 | 25.5 | 0 | 2116.5 | 0
45 | PVC 24-IN SD | LF | 214 | 45 | 9630 |  | 0 | 220 | 9900 | 220 | 9900 | 102.8% | X | 270 | 6 | 220 | 45 | PVC 24-IN SD | LF | 45 | 6 | 0 | 270 | 0
46 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [5 empty] | 0 | 0 | 0 | [5 empty] | 46 | ITEM NOT USED IN THIS SCHEDULE | EA
47 | 54-IN MANHOLE - SD | EA | 1 | 3460 | 3460 |  | 0 | 1 | 3460 | 1 | 3460 | 100% | X | 0 | 0 | 1 | 47 | 54-IN MANHOLE - SD | EA | 3460 | 0 | 0 | 0 | 0
48 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [5 empty] | 0 | 0 | 0 | [5 empty] | 48 | ITEM NOT USED IN THIS SCHEDULE | EA
49 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 49 | ITEM NOT USED IN THIS SCHEDULE | EA
50 | 48-IN COMBINATION MANHOLE - SD | EA | 2 | 2395 | 4790 |  | 0 | 1 | 2395 | 1 | 2395 | 50% | X | -2395 | -1 | 1 | 50 | 48-IN COMBINATION MANHOLE - SD | EA | 2395 | 0 | -1 | 0 | -2395
51 | 54-IN COMBINATION MANHOLE - SD | EA | 1 | 3200 | 3200 |  | 0 | 1 | 3200 | 1 | 3200 | 100% | X | 0 | 0 | 1 | 51 | 54-IN COMBINATION MANHOLE - SD | EA | 3200 | 0 | 0 | 0 | 0
52 | INLETS - TYPE III / 30-IN BARREL | EA | 3 | 1765 | 5295 |  | 0 | 3 | 5295 | 3 | 5295 | 100% | X | 0 | 0 | 3 | 52 | INLETS - TYPE III / 30-IN BARREL | EA | 1765 | 0 | 0 | 0 | 0
53 | CONNECT TO EXISTING SD | EA | 4 | 250 | 1000 |  | 0 | 4 | 1000 | 4 | 1000 | 100% | X | 0 | 0 | 4 | 53 | CONNECT TO EXISTING SD | EA | 250 | 0 | 0 | 0 | 0
54 | IRRIGATION CROSSING | LS | 1 | 7915 | 7915 |  | 0 | 1 | 7915 | 1 | 7915 | 100% | X | 0 | 0 | 1 | 54 | IRRIGATION CROSSING | LS | 7915 | 0 | 0 | 0 | 0
55 | STRIPING EPOXY PAINT (YELLOW) 4-IN | LF | 5420 | 0.35 | 1897 |  | 0 | 5420 | 1897 | 5420 | 1897 | 100% | X | 0 | 0 | 5420 | 55 | STRIPING EPOXY PAINT (YELLOW) 4-IN | LF | 0.35 | 0 | 0 | 0 | 0
56 | ITEM NOT USED IN THIS SCHEDULE | LF | 0 | [13 empty] | 56 | ITEM NOT USED IN THIS SCHEDULE | LF
57 | STRIPING EPOXY PAINT (WHITE) 8-IN | LF | 235 | 0.7 | 164.5 |  | 0 | 235 | 164.5 | 235 | 164.5 | 100% | X | 0 | 0 | 235 | 57 | STRIPING EPOXY PAINT (WHITE) 8-IN | LF | 0.7 | 0 | 0 | 0 | 0
58 | ITEM NOT USED IN THIS SCHEDULE | LF | 0 | [13 empty] | 58 | ITEM NOT USED IN THIS SCHEDULE | LF
59 | STRIPING EPOXY PAINT (WHITE) 24-IN | LF | 100 | 6.5 | 650 |  | 0 | 100 | 650 | 100 | 650 | 100% | X | 0 | 0 | 100 | 59 | STRIPING EPOXY PAINT (WHITE) 24-IN | LF | 6.5 | 0 | 0 | 0 | 0
60 | STRIPING EPOXY PAINT - WORDS & SYM | SF | 345 | 3.25 | 1121.25 |  | 0 | 345 | 1121.25 | 345 | 1121.25 | 100% | X | 0 | 0 | 345 | 60 | STRIPING EPOXY PAINT - WORDS & SYM | SF | 3.25 | 0 | 0 | 0 | 0
61 | CURB PAINT (YELLOW) | GAL | 5 | 110 | 550 | 5 | 550 | 0 | 0 | 5 | 550 | 100% | X | 0 | 0 | 5 | 61 | CURB PAINT (YELLOW) | GAL | 110 | 0 | 0 | 0 | 0
62 | RESET MAILBOX | EA | 2 | 240 | 480 | 1 | 240 | 3 | 720 | 4 | 960 | 200% | X | 480 | 2 | 4 | 62 | RESET MAILBOX | EA | 240 | 2 | 0 | 480 | 0
63 | RESET MULTI-UNIT MAILBOX | EA | 1 | 390 | 390 |  | 0 | 1 | 390 | 1 | 390 | 100% | X | 0 | 0 | 1 | 63 | RESET MULTI-UNIT MAILBOX | EA | 390 | 0 | 0 | 0 | 0
64 | PRIVATE IRRIGATION ADJUSTMENT | LS | 1 | 3840 | 3840 |  | 0 | 1 | 3840 | 1 | 3840 | 100% | X | 0 | 0 | 1 | 64 | PRIVATE IRRIGATION ADJUSTMENT | LS | 3840 | 0 | 0 | 0 | 0
65 | SIGNS-INSTALLED | EA | 22 | 395 | 8690 | 1 | 395 | 21 | 8295 | 22 | 8690 | 100% | X | 0 | 0 | 22 | 65 | SIGNS-INSTALLED | EA | 395 | 0 | 0 | 0 | 0
66 | RESET SIGN | EA | 5 | 320 | 1600 |  | 0 | 5 | 1600 | 5 | 1600 | 100% | X | 0 | 0 | 5 | 66 | RESET SIGN | EA | 320 | 0 | 0 | 0 | 0
67 | TEMPORARY FENCE | LF | 370 | 4.25 | 1572.5 |  | 0 | 370 | 1572.5 | 370 | 1572.5 | 100% | X | 0 | 0 | 370 | 67 | TEMPORARY FENCE | LF | 4.25 | 0 | 0 | 0 | 0
68 | FENCE | LF | 370 | 15 | 5550 |  | 0 | 350 | 5250 | 350 | 5250 | 94.59% | X | -300 | -20 | 350 | 68 | FENCE | LF | 15 | 0 | -20 | 0 | -300
69 | NEW FIRE HYDRANT ASSEMBLY | EA | 2 | 3050 | 6100 |  | 0 | 2 | 6100 | 2 | 6100 | 100% | X | 0 | 0 | 2 | 69 | NEW FIRE HYDRANT ASSEMBLY | EA | 3050 | 0 | 0 | 0 | 0
70 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 70 | ITEM NOT USED IN THIS SCHEDULE | EA
71 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 71 | ITEM NOT USED IN THIS SCHEDULE | EA
72 | ITEM NOT USED IN THIS SCHEDULE | LF | 0 | [13 empty] | 72 | ITEM NOT USED IN THIS SCHEDULE | LF
73 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 73 | ITEM NOT USED IN THIS SCHEDULE | EA
74 | ITEM NOT USED IN THIS SCHEDULE | SF | 0 | [13 empty] | 74 | ITEM NOT USED IN THIS SCHEDULE | SF
75 | ITEM NOT USED IN THIS SCHEDULE | LF | 0 | [13 empty] | 75 | ITEM NOT USED IN THIS SCHEDULE | LF
76 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 76 | ITEM NOT USED IN THIS SCHEDULE | EA
77 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 77 | ITEM NOT USED IN THIS SCHEDULE | EA
78 | ITEM NOT USED IN THIS SCHEDULE | LF | 0 | [13 empty] | 78 | ITEM NOT USED IN THIS SCHEDULE | LF
79 | ITEM NOT USED IN THIS SCHEDULE | CY | 0 | [13 empty] | 79 | ITEM NOT USED IN THIS SCHEDULE | CY
80 | ITEM NOT USED IN THIS SCHEDULE | CY | 0 | [13 empty] | 80 | ITEM NOT USED IN THIS SCHEDULE | CY
81 | EXPLORATORY EXCAVATION - SMALL CREW | HRS | 5 | 205 | 1025 |  | 0 | 0 | 0 | 0 | 0 | 0% | X | -1025 | -5 | 0 | 81 | EXPLORATORY EXCAVATION - SMALL CREW | HRS | 205 | 0 | -5 | 0 | -1025
82 | EXPLORATORY EXCAVATION - LARGE CREW | HRS | 5 | 310 | 1550 |  | 0 | 5.5 | 1705 | 5.5 | 1705 | 110% | X | 155 | 0.5 | 5.5 | 82 | EXPLORATORY EXCAVATION - LARGE CREW | HRS | 310 | 0.5 | 0 | 155 | 0
TOTAL SCHEDULE 1 |  |  |  |  | 578358.75 |  | 8440.5 |  | 611597.82 |  | 620038.32 | 107.2% |  | 41679.57 |  |  |  | Subtotal |  |  |  |  | 71202.795 | -29523.225
Schedule 2 | [16 empty] | Schedule 2
1 | MOBILIZATION | LS | 1 | 22500 | 22500 |  | 0 | 1 | 22500 | 1 | 22500 | 100% | X | 0 | 0 | 1 | 1 | MOBILIZATION | LS | 22500 | 0 | 0 | 0 | 0
2 | TAXES, BONDS, AND INSURANCE | LS | 1 | 7170 | 7170 |  | 0 | 1 | 7170 | 1 | 7170 | 100% | X | 0 | 0 | 1 | 2 | TAXES, BONDS, AND INSURANCE | LS | 7170 | 0 | 0 | 0 | 0
3 | TRAFFIC CONTROL | LS | 1 | 42100 | 42100 |  | 0 | 1 | 42100 | 1 | 42100 | 100% | X | 0 | 0 | 1 | 3 | TRAFFIC CONTROL | LS | 42100 | 0 | 0 | 0 | 0
4 | CLEARING AND GRUBBING | LS | 1 | 85000 | 85000 |  | 0 | 1 | 85000 | 1 | 85000 | 100% | X | 0 | 0 | 1 | 4 | CLEARING AND GRUBBING | LS | 85000 | 0 | 0 | 0 | 0
5 | REMOVE PAVEMENT | SY | 9700 | 3 | 29100 |  | 0 | 10122.36 | 30367.08 | 10122.36 | 30367.08 | 104.4% | X | 1267.08 | 422.36 | 10122.36 | 5 | REMOVE PAVEMENT | SY | 3 | 422.36 | 0 | 1267.08 | 0
6 | COLD MILLING | SY | 450 | 12.5 | 5625 |  | 0 | 749 | 9362.5 | 749 | 9362.5 | 166.4% | X | 3737.5 | 299 | 749 | 6 | COLD MILLING | SY | 12.5 | 299 | 0 | 3737.5 | 0
7 | REMOVE CURB AND GUTTER | LF | 1580 | 3.5 | 5530 | 15 | 52.5 | 1613.2 | 5646.2 | 1628.2 | 5698.7 | 103.1% | X | 168.7 | 48.2 | 1628.2 | 7 | REMOVE CURB AND GUTTER | LF | 3.5 | 48.2 | 0 | 168.7 | 0
8 | CONCRETE FLATWORK REMOVAL | SY | 420 | 9.25 | 3885 | 10 | 92.5 | 770.24 | 7124.72 | 780.24 | 7217.22 | 185.8% | X | 3332.22 | 360.24 | 780.24 | 8 | CONCRETE FLATWORK REMOVAL | SY | 9.25 | 360.24 | 0 | 3332.22 | 0
9 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 9 | ITEM NOT USED IN THIS SCHEDULE | EA
10 | REMOVE IRRIGATION STRUCTURES | LS | 1 | 3975 | 3975 |  | 0 | 1 | 3975 | 1 | 3975 | 100% | X | 0 | 0 | 1 | 10 | REMOVE IRRIGATION STRUCTURES | LS | 3975 | 0 | 0 | 0 | 0
11 | REMOVE SIGNS | EA | 7 | 38 | 266 |  | 0 | 20 | 760 | 20 | 760 | 285.7% | X | 494 | 13 | 20 | 11 | REMOVE SIGNS | EA | 38 | 13 | 0 | 494 | 0
12 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 12 | ITEM NOT USED IN THIS SCHEDULE | EA
13 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 13 | ITEM NOT USED IN THIS SCHEDULE | EA
14 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 14 | ITEM NOT USED IN THIS SCHEDULE | EA
15 | ADJUST MANHOLE | EA | 34 | 190 | 6460 | 2 | 380 | 32 | 6080 | 34 | 6460 | 100% | X | 0 | 0 | 34 | 15 | ADJUST MANHOLE | EA | 190 | 0 | 0 | 0 | 0
16 | ADJUST WATER VALVE | EA | 40 | 295 | 11800 | 11 | 3245 | 29 | 8555 | 40 | 11800 | 100% | X | 0 | 0 | 40 | 16 | ADJUST WATER VALVE | EA | 295 | 0 | 0 | 0 | 0
17 | ADJUST GAS VALVE | EA | 2 | 410 | 820 |  | 0 | 4 | 1640 | 4 | 1640 | 200% | X | 820 | 2 | 4 | 17 | ADJUST GAS VALVE | EA | 410 | 2 | 0 | 820 | 0
18 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 18 | ITEM NOT USED IN THIS SCHEDULE | EA
19 | ADJUST FIRE HYDRANT | EA | 2 | 825 | 1650 |  | 0 | 0 | 0 | 0 | 0 | 0% | X | -1650 | -2 | 0 | 19 | ADJUST FIRE HYDRANT | EA | 825 | 0 | -2 | 0 | -1650
20 | RELOCATE CURB STOP | EA | 53 | 870 | 46110 |  | 0 | 47 | 40890 | 47 | 40890 | 88.68% | X | -5220 | -6 | 47 | 20 | RELOCATE CURB STOP | EA | 870 | 0 | -6 | 0 | -5220
21 | RELOCATE FIRE HYDRANT | EA | 5 | 1775 | 8875 |  | 0 | 6 | 10650 | 6 | 10650 | 120% | X | 1775 | 1 | 6 | 21 | RELOCATE FIRE HYDRANT | EA | 1775 | 1 | 0 | 1775 | 0
22 | RESET SURVEY MONUMENT | EA | 5 | 365 | 1825 | 5 | 1825 | 0 | 0 | 5 | 1825 | 100% | X | 0 | 0 | 5 | 22 | RESET SURVEY MONUMENT | EA | 365 | 0 | 0 | 0 | 0
23 | EXCAVATION UNCLASSIFIED | CY | 8030 | 8.75 | 70262.5 |  | 0 | 8030 | 70262.5 | 8030 | 70262.5 | 100% | X | 0 | 0 | 8030 | 23 | EXCAVATION UNCLASSIFIED | CY | 8.75 | 0 | 0 | 0 | 0
24 | ITEM NOT USED IN THIS SCHEDULE | CY | 0 | [13 empty] | 24 | ITEM NOT USED IN THIS SCHEDULE | CY
25 | TEMPORARY EROSION CONTROL | LS | 1 | 4850 | 4850 |  | 0 | 1 | 4850 | 1 | 4850 | 100% | X | 0 | 0 | 1 | 25 | TEMPORARY EROSION CONTROL | LS | 4850 | 0 | 0 | 0 | 0
26 | CRUSHED AGGREGATE COURSE | CY | 4740 | 13 | 61620 |  | 0 | 4404 | 57252 | 4404 | 57252 | 92.91% | X | -4368 | -336 | 4404 | 26 | CRUSHED AGGREGATE COURSE | CY | 13 | 0 | -336 | 0 | -4368
27 | PLANT MIX BIT SURF GR B-MOD | TON | 3610 | 26 | 93860 |  | 0 | 3626.6 | 94291.6 | 3626.6 | 94291.6 | 100.5% | X | 431.6 | 16.6 | 3626.6 | 27 | PLANT MIX BIT SURF GR B-MOD | TON | 26 | 16.6 | 0 | 431.6 | 0
28 | ASPHALT CEMENT PG 64-22 | TON | 195 | 520 | 101400 |  | 0 | 195.8 | 101816 | 195.8 | 101816 | 100.4% | X | 416 | 0.8 | 195.8 | 28 | ASPHALT CEMENT PG 64-22 | TON | 520 | 0.8 | 0 | 416 | 0
29 | EMULSIFIED ASPHALT SS-1 | GAL | 990 | 3 | 2970 |  | 0 | 990 | 2970 | 990 | 2970 | 100% | X | 0 | 0 | 990 | 29 | EMULSIFIED ASPHALT SS-1 | GAL | 3 | 0 | 0 | 0 | 0
30 | CONCRETE CURB AND GUTTER/LAYDOWN CURB | LF | 8670 | 10.75 | 93202.5 | 38 | 408.5 | 10131.7 | 108915.775 | 10169.7 | 109324.275 | 117.3% | X | 16121.775 | 1499.7 | 10169.7 | 30 | CONCRETE CURB AND GUTTER/LAYDOWN CURB | LF | 10.75 | 1499.7 | 0 | 16121.775 | 0
31 | CONCRETE SIDEWALK (4-INCH) | SF | 16200 | 3.5 | 56700 | 200 | 700 | 29040.88 | 101643.08 | 29240.88 | 102343.08 | 180.5% | X | 45643.08 | 13040.88 | 29240.88 | 31 | CONCRETE SIDEWALK (4-INCH) | SF | 3.5 | 13040.88 | 0 | 45643.08 | 0
32 | CONCRETE SIDEWALK (6-INCH) | SF | 1530 | 4.75 | 7267.5 |  | 0 | 1415 | 6721.25 | 1415 | 6721.25 | 92.48% | X | -546.25 | -115 | 1415 | 32 | CONCRETE SIDEWALK (6-INCH) | SF | 4.75 | 0 | -115 | 0 | -546.25
33 | ASPHALT PATH | SY | 2750 | 17 | 46750 |  | 0 | 2784.16 | 47330.72 | 2784.16 | 47330.72 | 101.2% | X | 580.72 | 34.16 | 2784.16 | 33 | ASPHALT PATH | SY | 17 | 34.16 | 0 | 580.72 | 0
34 | CONCRETE PEDESTRIAN RAMP (6-INCH) | SF | 4770 | 5.75 | 27427.5 |  | 0 | 4582.6 | 26349.95 | 4582.6 | 26349.95 | 96.07% | X | -1077.55 | -187.4 | 4582.6 | 34 | CONCRETE PEDESTRIAN RAMP (6-INCH) | SF | 5.75 | 0 | -187.4 | 0 | -1077.55
35 | DETECTABLE WARNING PANELS | SF | 416 | 26 | 10816 |  | 0 | 336 | 8736 | 336 | 8736 | 80.77% | X | -2080 | -80 | 336 | 35 | DETECTABLE WARNING PANELS | SF | 26 | 0 | -80 | 0 | -2080
11 | CONCRETE VALLEY GUTTER (6-INCH) | SF | 360 | 6.5 | 2340 |  | 0 | 218.9 | 1422.85 | 218.9 | 1422.85 | 60.81% | X | -917.15 | -141.1 | 218.9 | 11 | CONCRETE VALLEY GUTTER (6-INCH) | SF | 6.5 | 0 | -141.1 | 0 | -917.15
37 | CONCRETE DRIVEWAY APPROACH (6-INCH) | SF | 5895 | 5.75 | 33896.25 |  | 0 | 7090.9 | 40772.675 | 7090.9 | 40772.675 | 120.3% | X | 6876.425 | 1195.9 | 7090.9 | 37 | CONCRETE DRIVEWAY APPROACH (6-INCH) | SF | 5.75 | 1195.9 | 0 | 6876.425 | 0
38 | DRIVEWAY-ASPHALT | SY | 900 | 19 | 17100 | 10 | 190 | 1188.88 | 22588.72 | 1198.88 | 22778.72 | 133.2% | X | 5678.72 | 298.88 | 1198.88 | 38 | DRIVEWAY-ASPHALT | SY | 19 | 298.88 | 0 | 5678.72 | 0
39 | DRIVEWAY-CONCRETE | SF | 910 | 5.75 | 5232.5 | 150 | 862.5 | 1917.78 | 11027.235 | 2067.78 | 11889.735 | 227.2% | X | 6657.235 | 1157.78 | 2067.78 | 39 | DRIVEWAY-CONCRETE | SF | 5.75 | 1157.78 | 0 | 6657.235 | 0
40 | ITEM NOT USED IN THIS SCHEDULE | LF | 0 | [13 empty] | 40 | ITEM NOT USED IN THIS SCHEDULE | LF
41 | RETAINING WALL ADA | SF | 25 | 25 | 625 |  | 0 | 15 | 375 | 15 | 375 | 60% | X | -250 | -10 | 15 | 41 | RETAINING WALL ADA | SF | 25 | 0 | -10 | 0 | -250
42 | ITEM NOT USED IN THIS SCHEDULE | LF | 0 | [13 empty] | 42 | ITEM NOT USED IN THIS SCHEDULE | LF
43 | PVC 12-IN SD | LF | 231 | 45 | 10395 |  | 0 | 266 | 11970 | 266 | 11970 | 115.2% | X | 1575 | 35 | 266 | 43 | PVC 12-IN SD | LF | 45 | 35 | 0 | 1575 | 0
44 | PVC 15-IN SD | LF | 65 | 67 | 4355 |  | 0 | 69 | 4623 | 69 | 4623 | 106.2% | X | 268 | 4 | 69 | 44 | PVC 15-IN SD | LF | 67 | 4 | 0 | 268 | 0
45 | PVC 24-IN SD | LF | 836 | 42.5 | 35530 |  | 0 | 837.3 | 35585.25 | 837.3 | 35585.25 | 100.2% | X | 55.25 | 1.3 | 837.3 | 45 | PVC 24-IN SD | LF | 42.5 | 1.3 | 0 | 55.25 | 0
46 | 48-IN MANHOLE - SD | EA | 5 | 2660 | 13300 |  | 0 | 5 | 13300 | 5 | 13300 | 100% | X | 0 | 0 | 5 | 46 | 48-IN MANHOLE - SD | EA | 2660 | 0 | 0 | 0 | 0
47 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 47 | ITEM NOT USED IN THIS SCHEDULE | EA
48 | 60-IN MANHOLE - SD | EA | 1 | 3322 | 3322 |  | 0 | 1 | 3322 | 1 | 3322 | 100% | X | 0 | 0 | 1 | 48 | 60-IN MANHOLE - SD | EA | 3322 | 0 | 0 | 0 | 0
49 | 96-IN MANHOLE - SD | EA | 1 | 8600 | 8600 |  | 0 | 1 | 8600 | 1 | 8600 | 100% | X | 0 | 0 | 1 | 49 | 96-IN MANHOLE - SD | EA | 8600 | 0 | 0 | 0 | 0
50 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 50 | ITEM NOT USED IN THIS SCHEDULE | EA
51 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 51 | ITEM NOT USED IN THIS SCHEDULE | EA
52 | INLETS - TYPE III / 30-IN BARREL | EA | 18 | 1530 | 27540 |  | 0 | 18 | 27540 | 18 | 27540 | 100% | X | 0 | 0 | 18 | 52 | INLETS - TYPE III / 30-IN BARREL | EA | 1530 | 0 | 0 | 0 | 0
53 | CONNECT TO EXISTING SD | EA | 9 | 250 | 2250 |  | 0 | 9 | 2250 | 9 | 2250 | 100% | X | 0 | 0 | 9 | 53 | CONNECT TO EXISTING SD | EA | 250 | 0 | 0 | 0 | 0
54 | ITEM NOT USED IN THIS SCHEDULE | LS | 0 | [13 empty] | 54 | ITEM NOT USED IN THIS SCHEDULE | LS
55 | STRIPING EPOXY PAINT (YELLOW) 4-IN | LF | 10500 | 0.35 | 3675 |  | 0 | 12853 | 4498.55 | 12853 | 4498.55 | 122.4% | X | 823.55 | 2353 | 12853 | 55 | STRIPING EPOXY PAINT (YELLOW) 4-IN | LF | 0.35 | 2353 | 0 | 823.55 | 0
56 | STRIPING EPOXY PAINT (WHITE) 4-IN | LF | 5000 | 0.35 | 1750 |  | 0 | 4975 | 1741.25 | 4975 | 1741.25 | 99.5% | X | -8.75 | -25 | 4975 | 56 | STRIPING EPOXY PAINT (WHITE) 4-IN | LF | 0.35 | 0 | -25 | 0 | -8.75
57 | STRIPING EPOXY PAINT (WHITE) 8-IN | LF | 340 | 0.7 | 238 |  | 0 | 320 | 224 | 320 | 224 | 94.12% | X | -14 | -20 | 320 | 57 | STRIPING EPOXY PAINT (WHITE) 8-IN | LF | 0.7 | 0 | -20 | 0 | -14
58 | STRIPING EPOXY PAINT (WHITE) 12-IN | LF | 150 | 3.25 | 487.5 |  | 0 | 100 | 325 | 100 | 325 | 66.67% | X | -162.5 | -50 | 100 | 58 | STRIPING EPOXY PAINT (WHITE) 12-IN | LF | 3.25 | 0 | -50 | 0 | -162.5
59 | STRIPING EPOXY PAINT (WHITE) 24-IN | LF | 500 | 6.5 | 3250 |  | 0 | 507 | 3295.5 | 507 | 3295.5 | 101.4% | X | 45.5 | 7 | 507 | 59 | STRIPING EPOXY PAINT (WHITE) 24-IN | LF | 6.5 | 7 | 0 | 45.5 | 0
60 | STRIPING EPOXY PAINT - WORDS & SYM | SF | 600 | 3.25 | 1950 |  | 0 | 495 | 1608.75 | 495 | 1608.75 | 82.5% | X | -341.25 | -105 | 495 | 60 | STRIPING EPOXY PAINT - WORDS & SYM | SF | 3.25 | 0 | -105 | 0 | -341.25
61 | CURB PAINT (YELLOW) | GAL | 2 | 110 | 220 | 2 | 220 | 0 | 0 | 2 | 220 | 100% | X | 0 | 0 | 2 | 61 | CURB PAINT (YELLOW) | GAL | 110 | 0 | 0 | 0 | 0
62 | RESET MAILBOX | EA | 42 | 240 | 10080 | 3 | 720 | 38 | 9120 | 41 | 9840 | 97.62% | X | -240 | -1 | 41 | 62 | RESET MAILBOX | EA | 240 | 0 | -1 | 0 | -240
63 | RESET MULTI-UNIT MAILBOX | EA | 9 | 390 | 3510 | 3 | 1170 | 6 | 2340 | 9 | 3510 | 100% | X | 0 | 0 | 9 | 63 | RESET MULTI-UNIT MAILBOX | EA | 390 | 0 | 0 | 0 | 0
64 | PRIVATE IRRIGATION ADJUSTMENT | LS | 1 | 10900 | 10900 | 0.5 | 5450 | 0.5 | 5450 | 1 | 10900 | 100% | X | 0 | 0 | 1 | 64 | PRIVATE IRRIGATION ADJUSTMENT | LS | 10900 | 0 | 0 | 0 | 0
65 | SIGNS-INSTALLED | EA | 34 | 430 | 14620 | 26 | 11180 | 9 | 3870 | 35 | 15050 | 102.9% | X | 430 | 1 | 35 | 65 | SIGNS-INSTALLED | EA | 430 | 1 | 0 | 430 | 0
66 | RESET SIGN | EA | 22 | 320 | 7040 | 20 | 6400 | 3 | 960 | 23 | 7360 | 104.5% | X | 320 | 1 | 23 | 66 | RESET SIGN | EA | 320 | 1 | 0 | 320 | 0
67 | ITEM NOT USED IN THIS SCHEDULE | LF | 0 | [13 empty] | 67 | ITEM NOT USED IN THIS SCHEDULE | LF
68 | ITEM NOT USED IN THIS SCHEDULE | LF | 0 | [13 empty] | 68 | ITEM NOT USED IN THIS SCHEDULE | LF
69 | ITEM NOT USED IN THIS SCHEDULE | EA | 0 | [13 empty] | 69 | ITEM NOT USED IN THIS SCHEDULE | EA
70 | 6" BEND - ALL ANGLES | EA | 4 | 180 | 720 |  | 0 | 4 | 720 | 4 | 720 | 100% | X | 0 | 0 | 4 | 70 | 6" BEND - ALL ANGLES | EA | 180 | 0 | 0 | 0 | 0
71 | 6" GATE VALVE AND BOX | EA | 1 | 960 | 960 |  | 0 | 1 | 960 | 1 | 960 | 100% | X | 0 | 0 | 1 | 71 | 6" GATE VALVE AND BOX | EA | 960 | 0 | 0 | 0 | 0
72 | 6" WATER MAIN | LF | 20 | 140 | 2800 |  | 0 | 71 | 9940 | 71 | 9940 | 355% | X | 7140 | 51 | 71 | 72 | 6" WATER MAIN | LF | 140 | 51 | 0 | 7140 | 0
73 | 6" CONNECTION WITH COUPLING | EA | 2 | 495 | 990 |  | 0 | 2 | 990 | 2 | 990 | 100% | X | 0 | 0 | 2 | 73 | 6" CONNECTION WITH COUPLING | EA | 495 | 0 | 0 | 0 | 0
74 | 2" INSULATION BOARD | SF | 80 | 9.25 | 740 |  | 0 | 408 | 3774 | 408 | 3774 | 510% | X | 3034 | 328 | 408 | 74 | 2" INSULATION BOARD | SF | 9.25 | 328 | 0 | 3034 | 0
75 | 12" WATER MAIN | LF | 27 | 140 | 3780 |  | 0 | 15 | 2100 | 15 | 2100 | 55.56% | X | -1680 | -12 | 15 | 75 | 12" WATER MAIN | LF | 140 | 0 | -12 | 0 | -1680
76 | 12" CONNECTION WITH COUPLING | EA | 2 | 1230 | 2460 |  | 0 | 2 | 2460 | 2 | 2460 | 100% | X | 0 | 0 | 2 | 76 | 12" CONNECTION WITH COUPLING | EA | 1230 | 0 | 0 | 0 | 0
77 | SLOTTED BARREL DRYWELL MANHOLE | EA | 1 | 2200 | 2200 |  | 0 | 1 | 2200 | 1 | 2200 | 100% | X | 0 | 0 | 1 | 77 | SLOTTED BARREL DRYWELL MANHOLE | EA | 2200 | 0 | 0 | 0 | 0
78 | 10" SDR 35 PERFORATED/SOLID PIPE | LF | 80 | 18 | 1440 |  | 0 | 54 | 972 | 54 | 972 | 67.5% | X | -468 | -26 | 54 | 78 | 10" SDR 35 PERFORATED/SOLID PIPE | LF | 18 | 0 | -26 | 0 | -468
79 | SIEWART LANE BOULDER PIT | CY | 90 | 55 | 4950 |  | 0 | 130 | 7150 | 130 | 7150 | 144.4% | X | 2200 | 40 | 130 | 79 | SIEWART LANE BOULDER PIT | CY | 55 | 40 | 0 | 2200 | 0
80 | SMALL BOULDER PIT | CY | 45 | 65 | 2925 |  | 0 | 45 | 2925 | 45 | 2925 | 100% | X | 0 | 0 | 45 | 80 | SMALL BOULDER PIT | CY | 65 | 0 | 0 | 0 | 0
81 | EXPLORATORY EXCAVATION - SMALL CREW | HRS | 10 | 205 | 2050 |  | 0 | 15 | 3075 | 15 | 3075 | 150% | X | 1025 | 5 | 15 | 81 | EXPLORATORY EXCAVATION - SMALL CREW | HRS | 205 | 5 | 0 | 1025 | 0
82 | EXPLORATORY EXCAVATION - LARGE CREW | HRS | 10 | 310 | 3100 |  | 0 | 0 | 0 | 0 | 0 | 0% | X | -3100 | -10 | 0 | 82 | EXPLORATORY EXCAVATION - LARGE CREW | HRS | 310 | 0 | -10 | 0 | -3100
TOTAL SCHEDULE2 |  |  |  |  | 1111138.25 |  | 32896 |  | 1167035.155 |  | 1199931.155 | 108% |  | 88792.905 |  |  |  | Subtotal |  |  |  |  | 110916.355 | -22123.45
T O T A L P R O J E C T |  |  |  |  | 1689497 |  | 41336.5 |  | 1778632.975 |  | 1819969.475 | 107.7% |  | 130472.475
Previous Change Orders
[17 empty] | CO 1 - 1 Install Wood Split Rail Fence (3-rail) |  | LF | 12.25 | 0 | 0 | 0 | 0
CHANGE ORDERS | [16 empty] | CO 1 - 2 Remove and Replace Irrigation Culvert |  | LF | 93 | 0 | 0 | 0 | 0
CO 1 - 1 Install Wood Split Rail Fence (3-rail) |  | LF | 510 | 12.25 | 6247.5 |  | 0 | 510 | 6247.5 | 510 | 6247.5 | 100% | X | 0 | 0 | 510 | CO 1 - 3 Reshape ditch bank |  | LS | 2050 | 0 | 0 | 0 | 0
CO 1 - 2 Remove and Replace Irrigation Culvert |  | LF | 30 | 93 | 2790 |  | 0 | 30 | 2790 | 30 | 2790 | 100% | X | 0 | 0 | 30 | CO 1 - 4 Repair Culvert |  | LS | 3220 | 0 | 0 | 0 | 0
CO 1 - 3 Reshape ditch bank |  | LS | 1 | 2050 | 2050 |  | 0 | 1 | 2050 | 1 | 2050 | 100% | X | 0 | 0 | 1 | CO 1 - 5 Install Temporary Buisness signs |  | EA | 490 | 0 | -1 | 0 | -490
CO 1 - 4 Repair Culvert |  | LS | 1 | 3220 | 3220 |  | 0 | 1 | 3220 | 1 | 3220 | 100% | X | 0 | 0 | 1 | CO 1 - 6 3/4 Crushed rock w/ fabric |  | SY | 3.2 | 0 | 0 | 0 | 0
CO 1 - 5 Install Temporary Buisness signs |  | EA | 3 | 490 | 1470 |  | 0 | 2 | 980 | 2 | 980 | 66.67% | X | -490 | -1 | 2
CO 1 - 6 3/4 Crushed rock w/ fabric |  | SY | 5320 | 3.2 | 17024 |  | 0 | 5320 | 17024 | 5320 | 17024 | 100% | X | 0 | 0 | 5320 | CO 2 - 1 Modify Storm Drain |  | LS | 4770.13 | 0 | 0 | 0 | 0
TOTAL CO - 1 |  |  |  |  | 32801.5 |  | 0 |  | 32311.5 |  | 32311.5 | 98.51% |  |  |  |  | CO 2 - 2 Repair Culvert |  | LS | 1702.8 | 0 | 0 | 0 | 0
CO 2 - 1 Modify Storm Drain |  | LS | 1 | 4770.13 | 4770.13 |  | 0 | 1 | 4770.13 | 1 | 4770.13 | 100% | X | 0 | 0 | 1
CO 2 - 2 Repair Culvert |  | LS | 1 | 1702.8 | 1702.8 |  | 0 | 1 | 1702.8 | 1 | 1702.8 | 100% | X | 0 | 0 | 1 | CO 3 - 1 Flowable Fill |  | LS | 1750 | 0 | 0 | 0 | 0
TOTAL CO - 2 |  |  |  |  | 6472.93 |  | 0 |  | 6472.93 |  | 6472.93 | 100% |  |  |  |  | CO 3 - 2 Remove and Reset Light Pole |  | LS | 2890 | 0 | 0 | 0 | 0
CO 3 - 1 Flowable Fill |  | LS | 1 | 1750 | 1750 |  | 0 | 1 | 1750 | 1 | 1750 | 100% | X | 0 | 0 | 1 | CO 3 - 3 Install Backflow Preventer |  | LS | 3300 | 0 | 0 | 0 | 0
CO 3 - 2 Remove and Reset Light Pole |  | LS | 1 | 2890 | 2890 | 0.5 | 1445 | 0.5 | 1445 | 1 | 2890 | 100% | X | 0 | 0 | 1 | CO 3 - 4 Install Barrel Sections |  | LS | 1920 | 0 | 0 | 0 | 0
CO 3 - 3 Install Backflow Preventer |  | LS | 1 | 3300 | 3300 |  | 0 | 1 | 3300 | 1 | 3300 | 100% | X | 0 | 0 | 1
CO 3 - 4 Install Barrel Sections |  | LS | 1 | 1920 | 1920 |  | 0 | 1 | 1920 | 1 | 1920 | 100% | X | 0 | 0 | 1 | CO 4 - 1 Additional Storm Drain Work |  | EA | 1 | 0 | -7755.23 | 0 | -7755.23
TOTAL CO - 3 |  |  |  |  | 9860 |  | 1445 |  | 8415 |  | 9860 | 100% |  |  |  |  | CO 4 - 2 Kuhlman Drive Fire Hydrant |  | EA | 1 | 0 | 0 | 0 | 0
CO 4 - 1 Additional Storm Drain Work |  | EA | 21100 | 1 | 21100 |  | 0 | 13344.77 | 13344.77 | 13344.77 | 13344.77 | 63.25% | X | -7755.23 | -7755.23 | 13344.77 | CO 4 - 3 Additional Work |  | LS | 4523.14 | 0 | 0 | 0 | 0
CO 4 - 2 Kuhlman Drive Fire Hydrant |  | EA | 3800 | 1 | 3800 |  | 0 | 3800 | 3800 | 3800 | 3800 | 100% | X | 0 | 0 | 3800 | CO 4 - 4 Addtional Tree Removals |  | LS | 6352.5 | 0 | 0 | 0 | 0
CO 4 - 3 Additional Work |  | LS | 1 | 4523.14 | 4523.14 |  | 0 | 1 | 4523.14 | 1 | 4523.14 | 100% | X | 0 | 0 | 1
CO 4 - 4 Addtional Tree Removals |  | LS | 1 | 6352.5 | 6352.5 |  | 0 | 1 | 6352.5 | 1 | 6352.5 | 100% | X | 0 | 0 | 1 | CO 5 - 1 Retaining Wall - Small Brick |  | SF | 17 | 0 | 0 | 0 | 0
TOTAL CO - 4 |  |  |  |  | 35775.64 |  | 0 |  | 28020.41 |  | 28020.41 | 78.32%
CO 5 - 1 Retaining Wall - Small Brick |  | SF | 405 | 17 | 6885 |  | 0 | 405 | 6885 | 405 | 6885 | 100% | X | 0 | 0 | 405 | CO 6 - 1 Traffic Control Loop - Repair |  | LS | 1480.5 | 0 | 0 | 0 | 0
TOTAL CO - 5 |  |  |  |  | 6885 |  | 0 |  | 6885 |  | 6885 | 100% |  |  |  |  | CO 6 - 2 Ditch Bank Stabilization |  | LS | 2000 | 0 | 0 | 0 | 0
CO 6 - 1 Traffic Control Loop - Repair |  | LS | 1 | 1480.5 | 1480.5 |  | 0 | 1 |  | 1 | 1480.5 | 100% | X | 0 | 0 | 1 |  | Subtotal |  |  |  |  | 0 | -8245.23
CO 6 - 2 Ditch Bank Stabilization |  | LS | 1 | 2000 | 2000 | 1 | 2000 | 0 |  | 1 | 2000 | 100% | X | 0 | 0 | 1
TOTAL CO - 6 |  |  |  |  | 3480.5 |  | 0 |  | 6885 |  | 3480.5 | 100%
R E V I S E D C O N T R A C T |  |  |  |  | 1784772.57 |  | 44781.5 |  | 1860737.815 |  | 1906999.815 | 106.8% |  | 122227.245 |  |  |  | TOTAL NET INCREASE / (DECREASE) |  |  |  |  | 182119.15 | -59891.905
[18 empty] | RECONCILING AMOUNT | [5 empty] | 122227.245
| TOTAL ADVANCED MATERIALS RECEIVED |  |  |  | 0
| LESS USED ON CONTRACT |  |  |  | 0
| MATERIALS ON HAND NOT USED |  |  |  | 0
| WORK COMPLETED TO DATE |  |  |  | 1906999.815 |  | C O N T R A C T T I M E |  | 150 Calendar Days |  | S T A R T / S T O P D A T E S
| TOTAL WORK AND MATERIALS |  |  |  | 1906999.815 |  | + or - Change Order |  | 11 |  | S T A R T |  | 2010-06-01
| DEDUCTIONS: | [5 empty] | Total Contract Time |  | 172 |  | S T O P
| LESS RETAINAGE |  |  |  | 95349.99 |  | Less Used |  | -40330 |  | WEATHER DAYS
| LESS TEST FAILURE DEDUCTIONS |  |  |  | 175 |  | Total Days Remaining |  | 40502 |  | ESTIMATED END
| LESS LIQUIDATED DAMAGES |  |  |  | 0 |  | Percent Of Time Used |  | -23448% |  | SUBST. CMPLTE. |  | 2010-11-09
| TOTAL DEDUCTIONS |  |  |  | 95524.99
| TOTAL EARNED TO DATE (INCL. 1% STATE TAX) |  |  |  | 1811474.825
| LESS PREVIOUS PAYMENTS (INCL. 1% STATE TAX) |  |  |  | 1767700.92 |  | I Hereby Certify These Quantities And Times To Be True And Correct:
| TOTAL THIS ESTIMATE (INCL. 1% STATE TAX) |  |  |  | 43773.91
| LESS 1% MONTANA TAX |  |  |  | 437.74 |  | Ken Ard |  |  |  | Contractor / Title
| TOTAL DUE CONTRACTOR THIS ESTIMATE |  |  |  | 43336.17 |  | CITY OF BILLINGS |  |  |  | DATE: