[image: image1.jpg]DATE:

SUBJECT:

RATIONALE/NEED:

RECOMMENDATION:

COST:

Hidalgo County Head Start Program

Policy Council Agenda

November 15, 2006

Presentation for Discussion and Approval for
Payment of Certificate of Payment #2 to
Centennial Contractors Enterprises, Inc., for the
Relocation of McAllen Il Head Start Center under
Purchase Order Ne 68040

This is payment #2 for construction work
performed by Centennial Contractors Enterprises,
Inc., an awarded vendor of the Cooperative
Purchasing Network (TCPN) for the relocation on
the McAllen Il Building.

Administration recommends approval

$43,026.45

RELATED INFORMATION INCLUDED: Application & Certification for

Payment

kokok ok ko ok ok ok ok ok ok ok ok od ok ok ok ok ko ok ok ok ok ok ok ok ok ok ok ko k ok ok ok ok ok ok ok ok ok kok ok ok ok ok kK

A A~

INITIATED BY: Ambrosio Tovar, Procurement Director

REVIEWED BY: Mr. Edmundo Garcia, Assistant Director/%

) ]
PROGRAM DIRECTOR’S APPROVAL: 7 srssss —~Zhprs. |





[image: image2.jpg]rike
ogden

' figueroa
orchitects allex

October 16, 2006

Mr. Ambrosio Tovar
Procurement

Hidalgo County

Head Start Program
P.0.Box 0117

Edinburg, Texas 78540-0117

RE:  Relocation of McAllen Head Start Bldg.
Hidalgo County

Dear Mr. Tovar,

Attached is Application for payment No.2 regarding subject project. We recommend payment of
$43,026.45.

Please pay directly to:

CENTENNIAL CONTRACTORS ENT. INC.
4909 E. GRIMES STE. 118
HARLINGEN, TEXAS 78550

Sincerely,

RIKE-OGDEN-FIGUEROA-ALLEX ARCHITECTS INC.

CZ5000 @ s

Luis A. Figueroa, AIA
Principal

LF/dt

Attachment




[image: image3.jpg]SRR R PRV )

AlA DOCUMENT G702 PAGEONEOF 2 PAGES 1

JWNER: Hidalgo County

Head Start Program
P.O.Box 0117
Edinburg.,TX 78540-0117
M CONTRACTOR:
Centennial Contractors Ent. Inc.
4909 E. Grimes Ste.118

Harlingen,TX 78550
TRACT FOR AJOC TCPN Area B

PROJECT: Relo. Of McAllen

Headstart Bldg., Hidalgo
County

VIA ARCHITECT: ROFA Architects
1007 Walnut Ave.
McAllen, TX 78501

APPLICATION NO 2 Distribution to:

OWNER
[ ]arcurtecr
PERIOD TO: 09/01/06 - 09/30/06 CONTRACTOR
[ JormEr
AUDITOR
PROJECT NOS: 68040
CONTRACT DATE  6/15/2006

'NTRACTOR'S APPLICATION FOR PAYMENT

cation is made for payment, as shown below, in connection with the Contract.

nuation Sheet, AIA Document G703, is attached.

UGINAL CONTRACT SUM $ 126,391.00
:t change by Change Orders $
INTRACT SUM TO DATE (Line | +2) 3 126,391.00
)TAL COMPLETED & STORED TO $ 77,895.00
DATE  (Column G on G703)
iTAINAGE:
) 5 % of Completed Work $ 3,894.75

(Column D +E on G703)
. % of Stored Material $ 4]

(Column F on G703) -

Total Retainage (Lines 5a + Sb or

Total in Column [ of G703) $ 3,894.75
JTAL EARNED LESS RETAINAGE « 3 74,000.25

(Line 4 Less Line 5 Total) =
:SS PREVIOUS CERTIFICATES FOR
YMENT (Line 6 from prior Certificate) 3 43,026.45
JRRENT PAYMENT DUE $ 30,973.80
\LANCE TO FINISH, INCLUDING RETAINAGE $ 52,390.75

(Line 3 less Line 6)

CHANGE ORDER SUMMARY ADDITIONS DEDUCTIONS

tal changes approved
previous months by Owner $0.00
tal approved this Month
ITALS $0.00 $0.00
T CHANGES by Change Order $0.00

The undersigned Contractor certifies that to the best of the Contractor's knowledge,
information and belief the Work covered by this Application for Payment has been
completed in accordance with the Contract Documents, that all amounts have been paid by
the Contractor for Work for which previous Certificates for Payment were issued and
payments received from the Owner, and that current payment shown herein is now due.

CONTRACTOR:

“\Nwl\Qmﬁ

Cn €
ALVN{VFNM«\\ Date:

ATDE FUENTES s
Public, State of T
zo”/w_thjBEm,o: Expires
september 20, 2009 .

Texas County of: m i
ed and swarn to before me this D2 “¥day of ﬂt‘.m\Av\’u 2c4
Notary Public: (X Lo .Durrk\rlh_qnx.v

SR

A7,

ARCHITECT'S CERTIFICATE EOR PAYMENT

In accordance with the Contract Documents, based on on-site observations and the data
comprising the application, the Architect certifies to the Owner that to the best of the
Architect's knowledge, information and be ef the Work has progressed as indicated,

the quality of the Work is in accordance with the Contract Documents, and the Contractor
is entitled to payment of the AMOUNT CERTIFIED.

s 30,9738°

(Anach explanation if amount certified differs from the amount applied. Initial all figures on this
Application and onthe Continuation Skeet thar are changed 1o conform with the amount certified.)

10:1%3- &

cale is not neg e. The AMOUNT CERTIFIED is payable only to the
Contractor named herein. Issuance, payment and acceptance of payment are without
prejudice to any rights of the Owner or Contractor under this Contract.

My Commission expires: &) (5 ¢ \ =

AMOUNT CERTIFIED

Date:

SUMENT G702 - APPLICATION AND CERTIFICATION FOR PAYMENT - 1992 EDITION - AIA® - @ 1992

3 may obtain v:

idation of this document by requesting a completed AIA Document D401 -

THE AMERICAN INSTITUTE OF ARCHITECTS, 1735 NEW YORK AVE., N.W., WASHINGTON, DC 20008-5292
Certification of Document's Authenticity from the Licensee.




[image: image4.jpg]Anonuayiny S,juawinaoq jo uoneayae) - Loya juswnooq uoyesedasd pajejdwios |

000% 00'96¥'8¥$ BEIT9 00°568°LLS 00'%709°'CES$ 00°16Z'St$ 00'16£'9Z1$
2%00°001 00TZ9'1$ 00729 1$ 00729'1$ spuog| 81
00°L0T'vS %0070 00°L0T'v$ JoqeT Ajquiasseay [eoroajg| 91
00'8€L°C$ %000 008€L'T$ [euatey A[quiasseayy eomoofg| ¢
%00°001 00'r1z'eS 00'11Z'z$ 00'112'8 10qeTT owa(T [eOLIRF| ]
%00°001 00 YLy TS 00 VLY 1S 00vLY' 1S [BLIRIBIN OwR( [e2t193[g| €]
00'988'1$ %00°0 00988°1$ loqu A[quissseay DVAH| z1
00°LST'T$ %000 00°LST'T$ [euey Alquiasseay DVAH| 11
%00°001 0061018 00°10'1$ 00°S10'T$ 10QeT owag DVAH| 01
%00°001 00°LL9S 00°LL9S 00°LL9% [BURIBIN OWRA DVAH| 6
00°586'v$ %000 00°586't+$ JoquT Ajquiasseay Suiquinig| g
00°€TE'ES %000 00°€ZE'es [eLRIBA A[quiasseay Buiquing| ,
%00°001 00'589'2$ 00'589'2$ 00'589°C$ Joqe] owaq Suiquinig| 9
%00°001 00°68L'1$ 0068L1$ 00°68L°1$ [eutey oulaq Suiquinid| ¢
_NU_ENIUHE
%00°001 00°€8t'LS 00°€8Y'LS 00°€8Y°LS Joqe Ajquiasseay Suipling | g
%00°001 00'886'¢$ 00'886't$ 00'886't$ [euatey Ajquiasseay Buipying | ,
%00°001 00620'%$ 00°620°v$ 00'620'v$ Joqe] uoneredaid n) Suiping| 9
%00°00T 00'989't$ 00'989'7$ 00989°C$ [eLatepy uoneredad D Fuipjmg]| ¢
00°00T°0£$ %000 00°00Z'0€$ 10qe jooy Alquiassey|
%00°001 00°€€1°0T$ 00°€€1°0ZS 00°€EET'0Z$ [eL21B A Jooy Ajquiasseay| ¢
%00°00T 0079Z'91% 00T9T'91$ 00292'91$ 10QET Jooy owa(| ¢
2007001 00 1+8'01% 00'1v8°01% 00'1¥8°01% [BUAEA Jooy owa(| |
owa(g ssnif p Jooy
@+3+a) @yoa
41va ol NI.LON) @+a)
(daLvy (5-2) daI0LS ANV agydo.Ls NOILLVOITddV
TTEVIIVA 41) HSINId OL +=9) Aa.LaTdNOD ATTLNESHAd doryad SIHL SNOIATYd WO ANTVA ON
ADVNIVLEY JONVIVE % IV.IOL STVIIELYI A3LITdNOD XIOM daINAgHdS HUOM 40 NOLLAINDSId L]
1 H 10} d 9 a o g v

07089 ‘ON LOFO¥d S.LOFLIHOAY
90/0€/60 - 90/T0/60 ‘0L AOIYAd
9002/52/6 ‘HLVA NOLLYII1ddY
4 ‘ON NOILVOI'lddV

T40z  $39vd 40 Iovd

“K1dde Rew swayt sur| 10y s3euTEIRl S[qBLIEA 213YM SIDBIUOD) UO | LUN[G7; 35[)

“IE[OP )SaIeaU Y} 01 PAILIS AIE SIUNOWIE *MO[aq SUONE[NGE; ug

“PRY2ENE ST UONEIYNIAD PauFIs S 1010B1UOD)

FulureIuod \INFNA YA 404 NOILLYDILLYED ANV NOILYII'ddV "Z0LD 1uawndoq vy

133HS NOILVNNILNOD L'vol





