## Ariel Hinojosa
Item No. | Bid Item No. | Item Description | Quantity | Unit | Unit Price | Amount Bid
ROADWAY
1 | 100 | Preparing ROW | 13.03 | STA | 600 | 7818
2 | 247 | Flex Base (RD DEL) TY "E" GR4 | 4054 | CY | 8.2 | 33242.8
3 | 251 | Reworking Fase Material (DC) (TY D CLII) | 4054 | SY | 2 | 8108
4 | 310 | Prime Coat (MC-30) | 811 | GAL | 5 | 4055
5 | 340 | Asph Conc ACP Surface (TY "D") (1.5") | 3475 | SY | 8 | 27800
6 | 501 | Barricades, Type III | 1 | EA | 750 | 750
7 | 502 | Barricades, Signs and Traffic Handling | 3 | LS | 1000 | 3000
8 | 530 | Turnouts (Asphalt, Concrete, Pavement) (PBS-2) | 30 | SY | 28 | 840
9 | 5249 | Temp Sedmt Cont Fence | 210 | LF | 5 | 1050
10 | 5249 | Temp Sedmt Cont Fence (Remove) | 210 | LF | 5 | 1050
11 |  | Relocate Mail Boxes | 1 | LS | 3000 | 3000
|  | SubTotal Base Bid |  |  |  | 90713.8
DRAINAGE
| 530 | Driveways (Asphalt, Concrete, Pavement) | 325 | SY | 28 | 9100
| 530 | Driveways (Concrete) | 195 | SY | 40 | 7800
| 556 | 15" ADS Corrugate Pipe | 450 | LF | 15 | 6750
| 556 | 18" RCP Culvert Pipe | 70 | LF | 25 | 1750
| 556 | Safety End Treatment | 2 | EA | 1000 | 2000
|  | SubTotal Drainage |  |  |  | 27400
|  | GrandTotal Roadwork Base Bid and Drainage |  |  |  | 118113.8
|  | Project Length: (LF) | 1310
|  | Cost Per Linear Feet @ $500K/mile: | 94.7
|  | Tot. Proj. Allowable (Cost per LF @$500K/mi X Proj. Lngth): | 124057
|  | Roadwork Allocation (Eng, Road Const and Contingency): | 121461.95
|  | Allowed Increase: | 2595.05 | Amt Inc.: | 30365.4875
|  | Road Construction Allocation: | 92800 |  | Drainage Allocation: |  | 24310
|  | Possible 25% Transfer In Other Projects: | 0 |  | Transfer In: A. Hinojosa Roadwork |  | 3090
|  | Contingency Transfer In: | 0 |  | Total Allocation and Transfer |  | 27400
|  | Total Allocation, 25% Transfer and Contingency Transfer | 92800 |  |  | Drainage Cost: | 27400
|  | Low Base Bid Roadwork | 90713.8 |  | Overrun/Underrun |  | 0
|  | Overrun/Underrun | 2086.2 | *
*Transferred out $3090.00 from Roadwork to Drainage
**Transferred in $3090.00 from Roadwork to Drainage