## A9R95C3
CHANGE ORDER NO. 1 TABULATION
HIDALGO COUNTY PRECINCT NO. 1 - LA MESA SUBDIVISION (C-CAP-10-357-12-13)
Item | Original Plan Qty | Change Order #1 Qty | Unit | Item Description | Unit Price | Revised Unit Price | Original Contract Cost | Change in Contract Cost of C.O.#1 | Revised Contract Cost after C.O.#1
(905) ROADWAY
100 | 26.07 |  | STA | PREPARING ROW | 500 |  | 13035 | 0 | 13035
110 | 232 | 99 | CY | EXCAVATION (ROADWAY) | 5 |  | 1160 | -665 | 495
132 | 1139 | 432 | CY | EMBANKMENT (FINAL)(DENS CONT)(TY C) | 10 |  | 11390 | -7070 | 4320
164 | 7487 |  | SY | CELL FBR MLCH SEED(PERM)(URBAN)(CLAY) | 0.4 |  | 2994.8 | 0 | 2994.8
168 | 375 |  | MG | VEGETATIVE WATERING | 3 |  | 1125 | 0 | 1125
247 | 8321 |  | SY | FL BS (CMP IN PLC)(TY E GR 4)(FNAL POS) | 5 |  | 41605 | 0 | 41605
251 | 8321 |  | SY | REWORK BS MTL (TY D)(5)(DENS CONT)" | 2 |  | 16642 | 0 | 16642
260 | 93.8 |  | TON | LIME(HYD,COM OR QK)(SLRY)OR QK(DRY) | 160 |  | 15008 | 0 | 15008
260 | 8321 |  | SY | LIME TRT(MIX EXST MATL & NEW BASE)(8)" | 2 |  | 16642 | 0 | 16642
310 | 1412 |  | GAL | PRIME COAT (MC-30) | 1 |  | 1412 | 0 | 1412
340 | 7055 |  | SY | D-GR HMA(METH) TY-D SAC-B PG76-22 | 7.5 |  | 52912.5 | 0 | 52912.5
420 | 5 |  | SY | CL A CONC (MISC)(4)" | 50 |  | 250 | 0 | 250
500 | 1 |  | LS | MOBILIZATION | 1000 |  | 1000 | 0 | 1000
502 | 4 |  | MO | BARRICADES, SIGNS AND TRAFFIC HANDLING | 700 |  | 2800 | 0 | 2800
666 | 4990 |  | LF | REFL PAV MRK TY I (W) 4 (SLD)(100MIL)" | 1 |  | 4990 | 0 | 4990
666 | 90 |  | LF | REFL PAV MRK TY I (W) 24(SLD)(100MIL)" | 6 |  | 540 | 0 | 540
666 | 510 |  | LF | REFL PAV MRK TY I (Y) 4 (BRK)(100MIL)" | 1 |  | 510 | 0 | 510
666 | 960 |  | LF | REFL PAV MRK TY I (Y) 4 (SLD)(100MIL)" | 1 |  | 960 | 0 | 960
|  |  |  | Total Roadway: |  |  | 184976.3 | -7735 | 177241.3
(906) DRAINAGE
110 | 0 | 135 | CY | EXCAVATION (ROADSIDE DITCH) | 5 |  | 0 | 675 | 675
132 | 0 | 752 | CY | EMBANKMENT (FINAL)(DENS CONT)(TY C) | 10 |  | 0 | 7520 | 7520
464 | 288 |  | LF | RC PIPE (CL III)(18 IN) | 30 |  | 8640 | 0 | 8640
506 | 156 |  | LF | TEMPORARY SEDIMENT CONTROL FENCE | 2 |  | 312 | 0 | 312
530 | 521 |  | SY | DRIVEWAYS (CONC) | 18 |  | 9378 | 0 | 9378
530 | 940 |  | SY | DRIVEWAYS (ACP) | 15 |  | 14100 | 0 | 14100
556 | 1275 |  | LF | 15 ADS CORRUGATED PIPE" | 15 |  | 19125 | 0 | 19125
|  |  |  | Total Drainage: |  |  | 51555 | 8195 | 59750
|  |  |  | GRAND TOTAL: |  |  | 236531.3 | 460 | 236991.3