## Acevedo #4
|  |  | Original Contract Amounts |  |  |  | Change Order 1
Item No. | Bid Item No. | Item Description | Unit | Original Quantities | Original Rates | Amount Bid | Revised Rates | Revised Quantities | Amount Increase/Decrease
ROADWAY
1 | 100 | Preparing ROW | STA | 31.35 | 1000 | 31350
2 | 247 | Flex Base (Complete in Place) TY "E" GR4 (8") | CY | 9766 | 6 | 58596
3 | 251 | Reworking Flex Material (DC) (TY D CLII) | SY | 9766 | 3.5 | 34181
4 | 310 | Prime Coat (MC-30) | GAL | 1957 | 4.25 | 8317.25
5 | 340 | Asph Conc ACP Surface (TY "D") (1.5") | SY | 8371 | 8.45 | 70734.95
6 | 502 | Barricades, Signs and Traffic Handling | MO | 3 | 1500 | 4500
7 | 530 | Turnouts (Asphalt, Concrete, Pavement) (PBS-2) | SY | 180 | 20 | 3600
9 |  | Relocate Mail Boxes | LS | 1 | 800 | 800
|  | SubTotal Base Bid |  |  |  | 212079.2
DRAINAGE
1 | 464 | 15" ADS Culvert Pipe | LF | 1970 | 20 | 39400
2 | 464 | RCP (CL III) (18") | LF | 420 | 30 | 12600
3 | 467 | Safety End Treatment (Pre-Cast) (Ty II) ( 18") RCP) (1:6) | EA | 12 | 800 | 9600
4 | 506 | Temp Sedmt Cont Fence (Install) | LF | 1040 | 3 | 3120
5 | 506 | Temp Sedmt Cont Fence (Remove) | LF | 1040 | 1 | 1040
6 | 530 | Driveways (Asphalt, Concrete, Pavement) | SY | 1400 | 25 | 35000
7 | 530 | Driveways (Concrete) | SY | 962 | 35 | 33670
|  | SubTotal Drainage |  |  |  | 134430
|  | GrandTotal Roadwork Base Bid and Drainage |  |  |  | 346509.2
|  | Project Length: (LF) | 3135
|  | Cost Per Linear Feet @ $500K/mile: | 94.7
|  | Tot. Proj. Allowable (Cost per LF @$500K/mi X Proj. Lngth): | 296884.5
|  | Roadwork Allocation (Eng, Road Const and Contingency): | 282198.55
|  | Allowed Increase: | 14685.95 | Amt Inc.: | 70549.6375
|  | Road Construction Allocation: | 209711.5 | * | Drainage Allocation: |  | 145460 | *
|  | Possible 25% Transfer In Other Projects: | 0 |  | Transfer In: Other Projects
|  | Contingency Transfer In: | 2367.7 |  | Total Allocation and Transfer |  | 145460
|  | Total Allocation, 25% Transfer and Contingency Transfer | 212079.2 |  |  | Drainage Cost: | 134430
|  | Low Base Bid Roadwork | 212079.2 |  | Overrun/Underrun |  | 11030
|  | Overrun/Underrun | 0 |  | * Expense report dated 07.11.2012
|  | Change Order |  |  |  | Change Order
|  | Road Construction Allocation: | 0 |  | Drainage Allocation: |  | 0
|  | Transfer In: | 0 |  | Transfer In: Other Projects
|  | Total Allocation, 25% Transfer and Contingency Transfer | 0 |  | Total Allocation and Transfer |  | 0
|  | Low Base Bid Roadwork After Change Order | 0 |  |  | Drainage Cost: | 0
|  | Overrun/Underrun | 0 |  | Overrun/Underrun |  | 0
** Expense report dated 07.11.2012