## Project Summary
Implementation Plan
Texas Conference of Urban Counties
Participating Member County : | Hidalgo - Phase II ICJS |  |  |  | Software Licenses |  |  |  |  | License Fee
CUC Enterprise License
Budget Letter Date: | Phase II Implementation Plan |  |  |  | Case Management
Last Updated: | 2012-05-15 |  |  |  | Probate & Mental Health | Yes | Included In CUC Enterprise License
[5 empty] | Civil & Family | Yes
Tyler Technologies Contact: | Steve Moerbe |  |  |  | Criminal | Yes
| Accounts Manager |  |  |  | Justice of the Peace | Yes
| Tyler Technologies |  |  |  | Prosecutor | Yes
6500 International Parkway, Suite 2000
| Plano, Texas 75093 |  |  |  | Additional Products - County License
| 972/713-3770 |  |  |  | Jail Management | Yes | Paid through CUC TechShare |  |  | 375000
| Steve.Moerbe@TylerTech.com |  |  |  | Law Enforcement/RMS | Yes | Paid through CUC TechShare |  |  | included
[5 empty] | Community Supervision | Yes
Major Assumptions |  |  |  |  | Hot Checks | Yes | Paid through CUC TechShare |  |  | 90000
*See Assumptions Detail for more information
[5 empty] | Total - Local County Licenses |  |  |  |  | 465000
Expected Project Duration
CUC Enterprise Products & Additional Products: | 10 | Months
|  | Months |  |  | Implementation Services |  | Original Hours | Adjusted Hours | Original Cost | Adjusted Cost
Total: | 10 | Months |  |  | Summary
[5 empty] | Project Management |  | 1295.8483 | 1225.1 | 187898.0035 | 177639.5
Project Management dedication: | 75% |  |  |  | Implementation Plan |  | 16 | 16 | 2320 | 2320
[5 empty] | Customization |  | 2777 | 2635 | 361010 | 342550
Number of Interfaces: | 1 |  |  |  | Interfaces* |  | 450 | 450 | 58500 | 58500
[5 empty] | Fit Analysis |  | 296 | 296 | 38480 | 38480
Data Conversion Approach: | Approach 1 - Standard conversion of TSG UNIX products |  |  |  | Data Conversion |  | 722 | 722 | 93860 | 93860
[5 empty] | Configuration & Consulting |  | 850 | 929.6323 | 110500 | 120852.2
[5 empty] | Training |  | 920 | 920 | 115000 | 115000
Training Approach: | Tyler to perform direct training to end-users |  |  |  | Go-Live Assistance |  | 700 | 700 | 87500 | 87500
Other Services
[5 empty] | Services Totals |  | 8026.8483 | 7893.7323 | 1055068.0035 | 1036701.7
Travel Allowance Assumptions | 3 | days/trip. | 415.6055 | est. days onsite.
|  |  | 138.5352 | est. trips. | Travel Allowance Budget |  |  | prev | 160717 | 88250
Overnight hotel required? | Yes
Air travel required? | Yes
[5 empty] | Total Software License & Implementation Services |  |  |  | Original | 1680785.0035
[5 empty] | Total Software License & Implementation Services |  |  |  | Adjusted | 1589951.7
Selected:
Approach 1 - Standard conversion of TSG UNIX products
Data Conversion Approaches
Approach 1 - Standard conversion of TSG UNIX products
Approach 2 - Standard data conversion by Tyler analysts
Approach 3 - Client to perform data conversion with Tyler assistance
Yes
No

## Services Detail
Phase II Implementation Plan- Services Detail
Phase II |  |  |  | Am 4
| Rate | Amend #3 Hours | Amend #3 Cost | Adjusted Hours | Adjusted Cost | Diff 3v4 |  | Rate | Amend #3 Hours | Amend #3 Cost | Adjusted Hous | Adjusted Cost | Diff 3v4
CUC Products | [6 empty] | Additional Products
Project Management | 145 | 1295.8483 | 187898.0035 | 1225.1 | 177639.5 | -70.7483 | Project Management | 145 | 0 | 0 | 0 | 0
Implementation Plan | 145 | 16 | 2320 | 16 | 2320 | 0
Customization | 130 | 2777 | 361010 | 2614.5 | 339885 | -162.5 | Customization | 130 | 0 | 0 | 20.5 | 2665 | 20.5
Interfaces* | 130 | 450 | 58500 | 450 | 58500 | 0
Courts
Probate & Mental Health (CC) |  | Hours | Cost | Adjusted |  |  | Jail Management |  | Hours | Cost | Adjusted
Fit Analysis | 130 | 0 | 0 | 0 | 0 |  | Fit Analysis | 130 | 80 | 10400 | 0 | 0 | -80
Data Conversion | 130 | 0 | 0 | 0 | 0 |  | Data Conversion | 130 | 220 | 28600 | 0 | 0 | -220
Interfaces | 130 | 0 | 0 | 0 | 0 |  | Interfaces | 130 | 0 | 0 | 0 | 0 | 0
Configuration & Consulting | 130 | 0 | 0 | 0 | 0 |  | Configuration & Consulting | 130 | 250 | 32500 | 0 | 0 | -250
Training | 125 | 0 | 0 | 0 | 0 |  | Training | 125 | 320 | 40000 | 0 | 0 | -320
Go-Live Assistance | 125 | 0 | 0 | 0 | 0 |  | Go-Live Assistance | 125 | 320 | 40000 | 0 | 0 | -320
Civil & Family (CC & DC) | [6 empty] | Law Enforcement / RMS
Fit Analysis | 130 | 0 | 0 | 0 | 0 |  | Fit Analysis | 130 | 40 | 5200 | 0 | 0 | -40
Data Conversion | 130 | 0 | 0 | 0 | 0 |  | Data Conversion | 130 | 150 | 19500 | 0 | 0 | -150
Interfaces | 130 | 0 | 0 | 0 | 0 |  | Interfaces | 130 | 0 | 0 | 0 | 0 | 0
Configuration & Consulting | 130 | 0 | 0 | 0 | 0 |  | Configuration & Consulting | 130 | 120 | 15600 | 14.75 | 1917.5 | -105.25
Training | 125 | 0 | 0 | 0 | 0 |  | Training | 125 | 120 | 15000 | 8.5 | 1062.5 | -111.5
Go-Live Assistance | 125 | 0 | 0 | 0 | 0 |  | Go-Live Assistance | 125 | 100 | 12500 | 0 | 0 | -100
Criminal (CC & DC) | [6 empty] | Probation
Fit Analysis | 130 | 120 | 15600 | 296 | 38480 | 176 | Fit Analysis | 130 | 0 | 0 | 0 | 0
Data Conversion | 130 | 220 | 28600 | 722 | 93860 | 502 | Data Conversion | 130 | 0 | 0 | 0 | 0
Interfaces | 130 | 0 | 0 | 0 | 0 | 0 | Interfaces | 130 | 0 | 0 | 0 | 0
Configuration & Consulting | 130 | 360 | 46800 | 914.8823 | 118934.7 | 554.8823 | Configuration & Consulting | 130 | 0 | 0 | 0 | 0
Training - CC | 125 | 320 | 40000 | 911.5 | 113937.5 | 591.5 | Training | 125 | 0 | 0 | 0 | 0
Go-Live Assistance | 125 | 160 | 20000 | 700 | 87500 | 540 | Go-Live Assistance | 125 | 0 | 0 | 0 | 0
Prosecutor | [6 empty] | Hot Checks
Fit Analysis | 130 | 40 | 5200 | 0 | 0 | -40 | Fit Analysis | 130 | 16 | 2080 | 0 | 0 | -16
Data Conversion | 130 | 72 | 9360 | 0 | 0 | -72 | Data Conversion | 130 | 60 | 7800 | 0 | 0 | -60
Interfaces | 130 | 0 | 0 | 0 | 0 | 0 | Interfaces | 130 | 0 | 0 | 0 | 0 | 0
Configuration & Consulting | 130 | 80 | 10400 | 0 | 0 | -80 | Configuration & Consulting | 130 | 40 | 5200 | 0 | 0 | -40
Training | 125 | 120 | 15000 | 0 | 0 | -120 | Training | 125 | 40 | 5000 | 0 | 0 | -40
Go-Live Assistance | 125 | 80 | 10000 | 0 | 0 | -80 | Go-Live Assistance | 125 | 40 | 5000 | 0 | 0 | -40
Justice of the Peace | [6 empty] | Other/Additional Services
Fit Analysis | 130 | 0 | 0 | 0 | 0
Data Conversion | 130 | 0 | 0 | 0 | 0
Interfaces | 130 | 0 | 0 | 0 | 0
Configuration & Consulting | 130 | 0 | 0 | 0 | 0
Training | 125 | 0 | 0 | 0 | 0
Go-Live Assistance | 125 | 0 | 0 | 0 | 0
Total Services - CUC Products |  | 6110.8483 | 810688.0035 | 7849.9823 | 1031056.7 |  | Total Services - Additional Products |  | 1916 | 244380 | 43.75 | 5645
[6 empty] | 1739.134 | [6 empty] | -1872.25 | -133.116
TOTALS BELOW | [9 empty] | 0
|  | Orig Hrs | Orig Cost | Adj. Hrs | Adj. Cost |  |  |  | Orig Hrs | Orig Cost | Adj. Hrs | Adj. Cost
Project Management |  | 1295.8483 | 187898.0035 | 1225.1 | 177639.5 |  | Project Management |  | 0 | 0 | 0 | 0
Implementation Plan |  | 16 | 2320 | 16 | 2320 |  | Implementation Plan
Customization |  | 2777 | 361010 | 2614.5 | 339885 |  | Customization |  | 0 | 0 | 20.5 | 2665
Interfaces |  | 450 | 58500 | 450 | 58500 |  | Interfaces |  | 0 | 0 | 0 | 0
Fit Analysis |  | 160 | 20800 | 296 | 38480 |  | Fit Analysis |  | 136 | 17680 | 0 | 0
Data Conversion |  | 292 | 37960 | 722 | 93860 |  | Data Conversion |  | 430 | 55900 | 0 | 0
Configuration & Consulting |  | 440 | 57200 | 914.8823 | 118934.7 |  | Configuration & Consulting |  | 410 | 53300 | 14.75 | 1917.5
Training |  | 440 | 55000 | 911.5 | 113937.5 |  | Training |  | 480 | 60000 | 8.5 | 1062.5
Go-Live Assistance |  | 240 | 30000 | 700 | 87500 |  | Go-Live Assistance |  | 460 | 57500 | 0 | 0
|  | 6110.8483 | 810688.0035 | 7849.9823 | 1031056.7 |  | Other Services |  |  |  |  | 0
[9 empty] | 1916 | 244380 | 43.75 | 5645
|  |  | 1055068.0035 |  | 1036701.7
18366.3035
|  | Orig Hrs | Orig Cost | Adj. Hrs | Adj. Cost
Project Management |  | 1295.8483 | 187898.0035 | 1225.1 | 177639.5
Implementation Plan |  | 16 | 2320 | 16 | 2320
Customization |  | 2777 | 361010 | 2635 | 342550
Interfaces |  | 450 | 58500 | 450 | 58500
Fit Analysis |  | 296 | 38480 | 296 | 38480
Data Conversion |  | 722 | 93860 | 722 | 93860
Configuration & Consulting |  | 850 | 110500 | 929.6323 | 120852.2
Training |  | 920 | 115000 | 920 | 115000
Go-Live Assistance |  | 700 | 87500 | 700 | 87500