## District Balances
Texas Department of Transportation
Pharr District - 21
Fund 7604 - Colonias Project Funding as of July 9, 2013
County | Contract Obligations Remaining as of 05/31/13 | District Balance as of 07/01/13 | Discrepancy | Comments
Brooks | 0.46 | 0.45 | 0.01
Cameron | 3000.74 | 0 | 3000.74 | Need to research balance.
Hidalgo* | 6839486.16 | 5752004.23 | 1087481.93 | Processed Invoices 53 & 54 however still have an $850.62 balance that needs to be researched. All projects are expected to be completed within the next 8 months.
Jim Hogg | 0 | 0 | 0 | Completed
Starr* | 340206.34 | 340209.49 | -3.15 | Amendment #12 deleted 1 project and added 2 project.
Willacy | 0 | 0 | 0 | Completed
Zapata | 176728.34 | 176728.34 | 0 | County Completed all projects - pending final billing.
Pharr District Totals | 7359422.04 | 6268942.51 | 1090479.53
*Counties actively working on projects.

## Hidalgo County
Detail # | TWDB ID # | Colonia Name | Project Length (mi) |  |  |  | Hidalgo County
Remaining Balances
|  |  |  | Authorized Project Amount |  |  | Drainage | Roadway | Total
|  |  |  | Drainage | Max. Roadway | Total | Balance | Balance | Amount
Active Projects
3C1080103 | M1080103 | Bernal Heights No. 1 -- Added Am. 5 (plans done in 2nd call) | 0.16 | 22744 | 62921.52 | 85665.52 | 20117.2 | 60322.9 | 80440.1
3C1080230 | M1080230 | Dimas No. 3 -- Added Am. 5 (plans done in 2nd call) | 0.43 | 117764 | 177785.13 | 295549.13 | 117764 | 169320.53 | 287084.53
3C1080600 | M1080600 | Randolph Barnett #1 -- X per Am. 1, added Am. 6 | 0.12 | 32650 | 61553.03 | 94203.03 | 32650 | 53098.05 | 85748.05
3C1080587 | M1080587 | Ramirez Subd. (comp. app.) -- X per Am. 1, added Am. 6 | 0.1 | 0 | 46753.53 | 46753.53 | 0 | 39510.57 | 39510.57
3C1080588 | M1080588 | Ramirez Subd. #2 (comp. app.) -- X per Am. 1, added Am. 6 | 0.1 | 41700 | 50000 | 91700 | 41700 | 41331.44 | 83031.44
3C1080589 | M1080589 | Ramirez Subd. #3 (comp. app.) -- X per Am. 1, added Am. 6 | 0.14 | 34650 | 71000 | 105650 | 34650 | 61130.16 | 95780.16
3C1080606 | M1080606 | Regal Estates -- X per Am. 1, added Am. 6 | 0.24 | 65200 | 121000 | 186200 | 65200 | 106078.9 | 171278.9
| M1080329 | Hoehn Drive Subd. | 1.6 | 105322 | 351700.63 | 457022.63 | 70167.15 | 287141.16 | 357308.31
1200182.06
New Projects
3C1080855 | M1080855 | Ash Country | 0.22 | 32400 | 97905.35 | 130305.35 | 32400 | 85861.96 | 118261.96
3C1080220 | M1080220 | Delta West Subd. | 0.76 | 41600 | 313968.53 | 355568.53 | 41600 | 279595.92 | 321195.92
3C1080388 | M1080388 | La Milpa -- Added Am 6 | 0.15 | 39520 | 59864.79 | 99384.79 | 39520 | 56103.96 | 95623.96
3C1080727 | M1080727 | Tiejerina Estates -- Added Am. 5 (plans done in 1st call) | 0.43 | 111307.45 | 163850.88 | 275158.33 | 111307.45 | 163637.09 | 274944.54
3C1080422 |  | Lorenzana Subdivision
3C1080314 |  | Heidelburg Subdivision
| M1080310 | Havana Lomas #4 | 0.21 | 28710 | 104890.95 | 133600.95 | 28710 | 104890.95 | 133600.95
| M1080311 | Havana Lomas #5 | 0.13 | 25150 | 65000 | 90150 | 25150 | 65000 | 90150
3C1080603 | M1080603 | Rankin Subdivision -- Added Am 6 | 0.55 | 304387.84 | 275000 | 579387.84 | 304387.84 | 239382.59 | 543770.43
3C1080260 | M1080260 | Engleman Estates -- Added Am 6 | 0.46 | 43954 | 155607.53 | 199561.53 | 43954 | 142975.95 | 186929.95
3C1080752 | M1080752 | Trenton Terrace | 0.27 | 140840 | 135000 | 275840 | 140840 | 105922.66 | 246762.66
3D1080536 | M1080536 | Palm Lake Estates #1 (both) | 1.28 | 57227 | 140622 | 197849 | 57227 | 140622 | 197849
3C1080780 | M1080780 | Vereda Tropical | 0.24 | 25660 | 119307.18 | 144967.18 | 25660 | 107305.89 | 132965.89
2342055.26
To Be Deleted
3C1080215 | M1080215 | De Anda Subd. (comp. app.) | 0.12 | 12600 | 51725.18 | 64325.18 | 12600 | 45466.79 | 58066.79
3C1080779 | M1080779 | Valley View Estates -- Added Am. 1 | 0.32 | 8368 | 136555.34 | 144923.34 | 8368 | 125603.25 | 133971.25
3C1080790 | M1080790 | Village Grove #2 | 0.26 | 0 | 42407.91 | 42407.91 | 0 | 37596.92 | 37596.92
3C1080348 | M1080348 | Jardin Terrace Subd. -- X per Am. 1, added Am. 6 | 0.3 | 55600 | 142044.99 | 197644.99 | 55600 | 142044.99 | 197644.99
427279.95
|  | Project Totals | [6 empty] | 3542237.32
|  | BCAP 3rd Call Available Balance | [6 empty] | 5336307.41
BCAP 3rd Call Unobligated Balance | [8 empty] | 1794070.09
*Updated spreadsheet on 10/02/13 - Removed Blue Star Enterprises #2 as per email from Agapito Vargas on 09/26/13 and added Havana Lomas #4 & #5.
*Updated spreadsheet on 10/04/13 - processed invoice #57.