## Regal Estates
|  |  | Original Contract Amounts |  |  |  | Change Order 1
Item No. | Bid Item No. | Item Description | Unit | Original Quantities | Original Rates | Amount Bid | Revised Rates | Revised Quantities | Amount Increase/Decrease
ROADWAY
1 | 100 | Preparing ROW | STA | 12.37 | 750 | 9277.5
2 | 247 | 8" Flex Base (Comp in Place) TY "E" GR4 | SY | 4216 | 6.25 | 26350
3 | 251 | Reworking Base Material (DC) (TY D 6") | SY | 4216 | 3 | 12648
4 | 310 | Prime Coat (MC-30) | GAL | 843 | 3.25 | 2739.75
5 | 340 | Asph Conc ACP Surface (TY "D") (1.5") | SY | 3645 | 9 | 32805
6 | 502 | Barricades, Signs and Traffic Handling | MO | 2 | 1000 | 2000
|  | SubTotal Base Bid |  |  |  | 85820.25
DRAINAGE
| 464 | RCP (CL III) (18") Culvert | LF | 70 | 30 | 2100
| 467 | Safety End Treatment | EA | 2 | 1000 | 2000
| 473 | 15" ADS Culvert Pipe | LF | 1100 | 27 | 29700
| 506 | Temp Sedmt Cont Fence (Install) | LF | 410 | 2.5 | 1025
| 506 | Temp Sedmt Cont Fence (Remove) | LF | 410 | 1 | 410
| 530 | Driveways (Asphalt, Concrete, Pavement) | SY | 372 | 9 | 3348
| 530 | Driveways (Concrete) | SY | 1007 | 40 | 40280
| 530 | Turnouts (Asphalt Concrete Pavement) (PBS-2) | SY | 30 | 9 | 270
|  | Relocate Mail Boxes | LS | 1 | 5000 | 5000
|  | SubTotal Drainage |  |  |  | 84133
|  | GrandTotal Roadwork Base Bid and Drainage |  |  |  | 169953.25
|  | Project Length: (LF) | 1267.2
|  | Cost Per Linear Feet @ $500K/mile: | 94.7
|  | Tot. Proj. Allowable (Cost per LF @$500K/mi X Proj. Lngth): | 120003.84
|  | Roadwork Allocation (Eng, Road Const and Contingency): | 121000
|  | Allowed Increase: | Inc. Not Allowed | Amt Inc.: | 0
|  | Road Construction Allocation: | 95564.69 |  | Drainage Allocation: |  | 65200
|  | Possible 25% Transfer In Other Projects: | 0 |  | Transfer In: Jardin Terrace Drng |  | 0
|  | Contingency Transfer In: | 0 |  | Total Allocation and Transfer |  | 65200
|  | Total Allocation, 25% Transfer and Contingency Transfer | 95564.69 |  |  | Drainage Cost: | 84133
|  | Low Base Bid Roadwork | 85820.25 |  | Overrun/Underrun |  | -18933
|  | Overrun/Underrun | 9744.44
|  | Change Order |  |  |  | Change Order
|  | Road Construction Allocation: | 0 |  | Drainage Allocation: |  | 0
|  | Transfer In: | 0 |  | Transfer In: Other Projects
|  | Total Allocation, 25% Transfer and Contingency Transfer | 0 |  | Total Allocation and Transfer |  | 0
|  | Low Base Bid Roadwork After Change Order | 0 |  |  | Drainage Cost: | 0
|  | Overrun/Underrun | 0 |  | Overrun/Underrun |  | 0